## Data
Valencia Medical Portal
Tasks | Start Date | Days Needed | Completion | Adjusted Length
Project Propsal | 2023-08-26 | 5 | 2023-09-01 | 6
Database Table | 2023-09-04 | 9 | 2023-09-15 | 11
Front-End Structuring | 2023-09-10 | 5 | 2023-09-15 | 5
Front-End Development | 2023-09-18 | 20 | 2023-10-16 | 28
Debugging Process | 2023-10-02 | 10 | 2023-10-16 | 14
Creating Relational User Tables | 2023-10-10 | 8 | 2023-10-20 | 10
Connecting Front-End Data to MySQL Tables | 2023-10-20 | 14 | 2023-11-09 | 20
Implement Additions to UML Diagrams for the Back-End | 2023-11-09 | 14 | 2023-11-29 | 20
Testing and Quality Assurance | 2023-11-29 | 2 | 2023-12-01 | 2
Final Deployment | 2023-12-01 | 0 | 2023-12-01 | 0
Formulas:
Completion = WORKDAY([Start Date],[Days Needed])